## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | DG 3/11/21
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | DG 3/11/21
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | DG 3/11/21
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | DG 3/11/21
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | DG 3/11/21
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | DG 3/11/21
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | DG 3/11/21
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | DG 3/11/21
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | DG 3/11/21
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | DG 3/11/21
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | DG 3/11/21
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | DG 3/11/21
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | DG 3/11/21
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | DG 3/11/21
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | DG 3/11/21
As a player I want to move a piece so that I can advannce the page and end my turn. | Given a valid space when it's my turn then I expect to move to that space. |  |  | Pass | KH Passed 3/29/21
| Given that it is my turn, when I want to make a move, I can pick up a piece that is droppable |  |  | Pass | KH Passed 3/29/21
| Given that it's a black space when I make a move then I expected my move to be valid |  |  | Pass | KH Passed 3/29/21
As a player I want to sign out so that I can exit the system. | Given I am not in a game when I want to leave the website then I should see the sign out button |  |  | Pass | KH Passed 3/29/21
| Given I am on the homepage when I want to sign out then I should be able to sign out |  |  | Pass | KH Passed 3/29/21
| Given I am in a game when I want to sign out then I should be able to sign out with the signout button and be redirected to home |  |  | Pass | KH 3/29/21 It is possible for an ajax excetion to be thrown. Sometimes works, sometimes does not
| Given I am in a game when I sign out then the other player should be redirected to home and the game gets deleted (End of Game Experience) |  |  | Pass | KH 3/29/21 It is possible for an ajax excetion to be thrown. Sometimes works, sometimes does not
As a player I want to make a single jump so that I can take one of my opponent's pieces. | Given that I jump over an enemy piece when I move, I can take the enemy piece |  |  | Pass | KH Passed 3/29/21
| Given that there is a valid space behind the opponent piece when I attempt to jump, then I should be able to successfully capture the piece |  |  | Pass | KH Passed 3/29/21
| Given that I have captured an enemy piece and there are no available jumps left, then my turn is over |  |  | Pass | KH Passed 3/29/21
As a player, I want to see a message and an exit button when the game it over, so that I can leave the game when the game ends | Given that the game is over when I click on the exit button then I am taken to the home page. |  |  | Pass | KH 3/29/21 It is possible for an ajax excetion to be thrown. Sometimes works, sometimes does not
| Given both Players haven't resigned, when there is no moves to be made by either Player, then the game transitions to game over |  |  | Pass | KH Passed 3/29/21
| Given a player has no remaining pieces when the game ends, then that player has lost and their opponent has won |  |  | Pass | KH Passed 3/29/21
As a player, I want other players to lose when resigning from a game so that players are more likely to finish games | Given that I want to exit when playing a game, then I have the option to resign |  |  | Pass | KH Passed 3/29/21
| Given that I resign a game when it is not finished, then I automatically lose |  |  | Pass | KH Passed 3/29/21
| Given my opponent resigns when playing a game, then I am declared the winner of the game and exit |  |  | Pass | KH Passed 3/29/21
As a Player, I want to watch replays of my previous games so that I can improve my checkers playing skills | Given that I am on the home screen, when I want to watch a replay, then I can see a button that allows me to watch replays
Given that I press the button on the home screen, when I press that replay button, then I am brought to a page that allows me to select the game I want to replay
Given that I am watching a replay when I selected a past game, then I am able to step through the moves made during the game one at a time
Given I am done with viewing when I am in the process of watching a replay, then I am able to return to the home screen at any time
As a player, I want to be able to spectate other players games, so that I can learn how to improve my checkers playing skills. | Given I am on the home screen when there is an active game, then I am able to spectate the game |  |  |  |  | Pass | KH Passed 4/15/21
| Given I am not in a game when I am signed in, then I can see the active games being played |  |  |  |  | Pass | KH Passed 4/15/21
| Given I am viewing the board when I am spectating a game, then I cannot make any moves |  |  |  |  | Pass | KH Passed 4/15/21
| Given I am spectating a game, when I want to exit spectator mode, then I can click the exit button that will return me to the home screen. |  |  |  |  | Pass | KH Passed 4/15/21
| Given I am spectating a game, when a move is made by a player, then I should see that move being played out. |  |  |  |  | Pass | KH Passed 4/15/21